## Question Bank
ID | Stakeholder / SME | Role | Discovery Area | Starting Hypothesis | Primary Question | Follow-up Probe | Evidence / Artifact Requested | Requirement Type | Priority | Phase | Decision / Output Expected | Status | Response / Notes | Assumption Confirmed? | Requirement Discovered | Action Owner
1 | Victor Ong | COO | Executive outcome | The core objective is to reduce risk created by the KYC backlog without weakening accountability. | Which outcome would make this initiative material to VGB? | How would leadership distinguish a useful POC from an interesting demo? | Executive success measures and remediation commitments | Business | High | MVP | Define executive success criteria | Not Asked
2 | Victor Ong | COO | Strategic priority | Backlog remediation, cost reduction and regulatory assurance may have different priorities. | Is the priority backlog remediation, structural cost reduction, regulatory assurance, or a combination? | If trade-offs are required, which objective wins? | Prioritized business outcomes | Business | High | MVP | Rank business outcomes | Not Asked
3 | Victor Ong | COO | Leadership demo | The demo must prove a controlled operational outcome, not general AI capability. | What would make the leadership demonstration credible? | Which case, metric or control must be visible? | Leadership demo expectations | Functional | High | MVP | Define demo acceptance | Not Asked
4 | Victor Ong | COO | Risk appetite | Certain failures would stop the project regardless of productivity benefit. | What risk or failure would stop the initiative? | Is the stop condition regulatory, customer, operational, security, or reputational? | Executive stop conditions | Risk / Control | High | MVP | Set stop conditions | Not Asked
5 | Victor Ong | COO | Expansion gate | Expansion should depend on evidence from the POC. | What evidence would justify expansion beyond the POC? | Who must agree that the evidence is sufficient? | Funding and approval criteria | Business | High | MVP | Define expansion gate | Not Asked
6 | Victor Ong | COO | Ownership | A named executive must own the production decision. | Who owns the decision to move from POC to production? | Which committees or control functions participate? | Decision and governance path | Ownership | High | MVP | Name decision owner | Not Asked
7 | Grace Lim | Head of Financial Crime Operations | Current workflow | The actual process differs from the documented process. | Show us a recent periodic review from queue entry to closure. | What happened next at each handoff? | Recent completed review and system walkthrough | Functional | High | MVP | Map actual workflow | Not Asked
8 | Grace Lim | Head of Financial Crime Operations | Bottleneck | Evidence collection and waiting may consume more time than final judgment. | Where did the analyst spend active time, and where did the case wait? | Which wait states recur across cases? | Timestamps, queue history and analyst walkthrough | Business | High | MVP | Identify principal bottleneck | Not Asked
9 | Grace Lim | Head of Financial Crime Operations | Slow case | Exceptions expose the real operating problem. | Show us a slow case and what happened next. | What information, approval or system dependency delayed it? | One abnormally slow review | Functional | High | MVP | Identify exception path | Not Asked
10 | Grace Lim | Head of Financial Crime Operations | QA rework | Narrative and evidence defects may contribute to backlog growth. | Show us a review returned by QA. What was missing or incorrect? | Could the defect have been detected before submission? | Returned review and QA comments | Functional | High | MVP | Define preventable rework | Not Asked
11 | Grace Lim | Head of Financial Crime Operations | Evidence collection | Analysts manually retrieve and reconcile information across sources. | Which sources were used in the selected case? | How did the analyst know which sources to check and which source was authoritative? | Source list and evidence package | Functional | High | MVP | Define retrieval scope | Not Asked
12 | Grace Lim | Head of Financial Crime Operations | Change detection | Comparison with prior KYC may be a repeatable AI-assisted task. | Show a case with a material change since the prior review. | Which differences mattered, and how was materiality determined? | Current and prior review pair | Functional | High | MVP | Define comparison task | Not Asked
13 | Grace Lim | Head of Financial Crime Operations | Narrative preparation | Drafting may be assistive while accountability remains human. | Show the source material and final narrative for the same case. | Which sections required judgment and what causes QA rejection? | Narrative template and completed example | Functional | High | MVP | Define drafting scope | Not Asked
14 | Grace Lim | Head of Financial Crime Operations | Human boundary | The first MVP should remain analyst-assist. | Which steps could a system prepare without analyst judgment? | Which recommendations or writes require confirmation? | Authority map for current workflow | Risk / Control | High | MVP | Classify AI authority | Not Asked
15 | Grace Lim | Head of Financial Crime Operations | User experience | The tool must fit the analyst workflow. | What should the analyst see before accepting an AI-generated draft or recommendation? | What would cause analysts to abandon it and work manually? | Current analyst screen and review checklist | Non-functional | High | MVP | Define analyst experience | Not Asked
16 | Grace Lim | Head of Financial Crime Operations | Demo scope | A single real case should demonstrate the MVP value. | What should the leadership demo prove to operations? | Which case is representative, safe and available? | Demo candidate case | Business | High | MVP | Select demo case | Not Asked
17 | Raj Menon | Deputy MLRO | Difficult judgment | Compliance boundaries are clearest in difficult cases. | Show us a difficult review where compliance judgment was required. | What made the case ambiguous? | Difficult historical review | Risk / Control | High | MVP | Identify judgment boundary | Not Asked
18 | Raj Menon | Deputy MLRO | Policy grounding | Recommendations must be traceable to policy and evidence. | Which policy and evidence supported the decision? | Which policy version applied and how was it selected? | Applicable policy and evidence package | Risk / Control | High | MVP | Define grounding requirements | Not Asked
19 | Raj Menon | Deputy MLRO | Escalation | Escalation criteria should be explicit and testable. | What events require escalation, and who owns the escalation? | Show the last case where this occurred. | Escalated case and escalation procedure | Functional | High | MVP | Define escalation rules | Not Asked
20 | Raj Menon | Deputy MLRO | Authority | AI actions require explicit classification. | Which AI-supported actions are acceptable, confirmation-gated or prohibited? | Classify retrieve, compare, summarize, recommend, write, execute and approve. | Approved authority matrix | Risk / Control | High | MVP | Approve control boundary | Not Asked
21 | Raj Menon | Deputy MLRO | Human review | Human approval must be meaningful rather than ceremonial. | What must an analyst see before accepting a recommendation? | What sources, rationale, uncertainty and policy references are required? | Review and approval checklist | Risk / Control | High | MVP | Define approval evidence | Not Asked
22 | Raj Menon | Deputy MLRO | Overrides | Disagreement and override behavior must be auditable. | What happens when the analyst disagrees with the system? | Must the original output and override reason be retained? | Override requirements | Risk / Control | High | MVP | Define override process | Not Asked
23 | Raj Menon | Deputy MLRO | Auditability | An auditor may need to reconstruct the decision. | What must be retained for each AI-assisted review? | Are prompt, context, tools, sources, model version and human edits required? | Audit retention requirements | Non-functional | High | MVP | Define audit record | Not Asked
24 | Raj Menon | Deputy MLRO | Stop conditions | Some errors are intolerable. | What error, omission or behavior would immediately stop rollout? | How should the system fail when evidence is incomplete or conflicting? | Compliance stop conditions | Risk / Control | High | MVP | Set compliance gate | Not Asked
25 | Raj Menon | Deputy MLRO | Evaluation | Historical cases should determine readiness. | Which cases should be included in the evaluation set? | Include routine, missing-data, conflicting-source, escalation and unauthorized-action cases? | Representative case set | Evaluation | High | MVP | Approve evaluation coverage | Not Asked
26 | Raj Menon | Deputy MLRO | Acceptance threshold | Readiness needs an explicit gate. | What result would be good enough for analyst-assisted use? | What result would block release even if average quality is high? | Acceptance and release criteria | Evaluation | High | MVP | Set release thresholds | Not Asked
27 | Ben Tan | Head of Data Platform Engineering | Source access | Each source must be tied to the selected case. | Show how an analyst accesses each source used in the selected case. | Is access API-based, database-based, document-based or UI-only? | Source-system walkthrough | Technical | High | MVP | Create source inventory | Not Asked
28 | Ben Tan | Head of Data Platform Engineering | Test data | The POC needs representative, authorized data. | Which sources expose APIs, test environments and representative data? | Can historical cases be de-identified or must synthetic data be used? | Test environment and data-access options | Technical | High | MVP | Define POC data set | Not Asked
29 | Ben Tan | Head of Data Platform Engineering | Data ownership | Every source needs an approval owner. | Who owns each required data source and access decision? | What approval lead time or dependency applies? | Data owner and approval list | Ownership | High | MVP | Assign data owners | Not Asked
30 | Ben Tan | Head of Data Platform Engineering | Runtime | The application must run on an approved platform. | Where may the POC and a future production service run? | Data center, approved cloud, Kubernetes, container platform or other standard? | Approved runtime standards | Non-functional | High | MVP | Select runtime | Not Asked
31 | Ben Tan | Head of Data Platform Engineering | Claude access | The approved model path is not yet known. | Is direct Anthropic access allowed, or must Claude be consumed through an approved cloud path? | Who owns model credentials and endpoint approval? | Approved AI provider pattern | Technical | High | MVP | Select model access path | Not Asked
32 | Ben Tan | Head of Data Platform Engineering | Region and residency | Prompts, inference and telemetry may be subject to location restrictions. | Where may runtime, model inference, prompts, responses, embeddings, traces and evaluations operate or be retained? | Which components must remain in Singapore? | Data-residency and processing rules | Non-functional | High | MVP | Define regional boundary | Not Asked
33 | Ben Tan | Head of Data Platform Engineering | Network | Model and tool calls may require controlled connectivity. | What network path is approved for model endpoints and internal tools? | Are internet access, allow-lists, proxies, gateways or private endpoints required? | Network and egress standards | Non-functional | High | MVP | Define connectivity pattern | Not Asked
34 | Ben Tan | Head of Data Platform Engineering | Identity | Authentication and downstream authorization must be separated. | Should tools act as the user or a service identity? | How are case-level or customer-level entitlements enforced? | Identity and authorization architecture | Security | High | MVP | Select execution identity | Not Asked
35 | Ben Tan | Head of Data Platform Engineering | Tool authorization | Tool access must not exceed user authorization. | How should each tool authenticate and enforce read or write scope? | Which actions require user confirmation or step-up authorization? | Tool authorization requirements | Security | High | MVP | Define tool permissions | Not Asked
36 | Ben Tan | Head of Data Platform Engineering | Logging | Observability must not leak restricted information. | What must be logged, and what must not appear in logs? | Who may view traces and how long are they retained? | Logging, redaction and retention standards | Non-functional | High | MVP | Define observability boundary | Not Asked
37 | Ben Tan | Head of Data Platform Engineering | Resilience | Partial failures should return safely to manual work. | What should happen if Claude or a source system is unavailable? | Should the review retry, resume, pause or fall back to manual processing? | Resilience and manual fallback requirements | Non-functional | High | MVP | Define failure behavior | Not Asked
38 | Ben Tan | Head of Data Platform Engineering | Feasibility blocker | One unresolved dependency may determine MVP scope. | What dependency is most likely to prevent an end-to-end POC? | Can the scope be adjusted to demonstrate value without it? | Dependency and constraint list | Technical | High | MVP | Set feasible MVP boundary | Not Asked
39 | Anna Cruz | Vendor Management | Current price | VGB evaluates economics per review. | Walk us through how VGB is charged for a periodic review today. | What does the fee include and exclude? | Current fee schedule | Commercial | High | MVP | Define vendor cost baseline | Not Asked
40 | Anna Cruz | Vendor Management | Pricing variation | Case complexity may affect the unit price. | Does pricing vary by case type, risk level or volume band? | Which mix should the POC business case use? | Pricing tiers and case mix | Commercial | High | MVP | Define comparison assumptions | Not Asked
41 | Anna Cruz | Vendor Management | Internal effort | Vendor price alone is not total cost. | What internal analyst and QA effort is outside the vendor fee? | How are rework and escalations accounted for? | Internal effort and labor assumptions | Commercial | High | MVP | Define total cost per review | Not Asked
42 | Anna Cruz | Vendor Management | Rework cost | Returned and exceptional cases may add material cost. | What rework, exception or escalation costs are material? | Can those costs be connected to actual case categories? | Rework and exception baseline | Commercial | High | MVP | Quantify avoidable cost | Not Asked
43 | Anna Cruz | Vendor Management | Contract constraints | Existing terms may restrict data use or replacement options. | What contractual restrictions affect data, integrations or replacement options? | When and how could the operating model change? | Relevant contract terms | Commercial | High | MVP | Identify contractual constraints | Not Asked
44 | Anna Cruz | Vendor Management | Commercial threshold | The business case needs a meaningful target. | What cost-per-completed-review result would be commercially meaningful? | Should the comparison include quality approval and rework? | Commercial acceptance measure | Commercial | High | MVP | Set business-case target | Not Asked
45 | KYC Analysts | Front-line reviewers | Workflow reality | The analyst experience will reveal undocumented workarounds. | Walk through the last review completed and show every system used. | Where was information copied, reconciled or re-entered? | Screen walkthrough and recent case | Functional | High | MVP | Validate actual task flow | Not Asked
46 | KYC Analysts | Front-line reviewers | Exceptions | Exception handling drives variability. | Show the last case where required information was missing. | What did the analyst do next and who was contacted? | Missing-information case | Functional | High | MVP | Map exception handling | Not Asked
47 | KYC Analysts | Front-line reviewers | Trust | AI output must be inspectable. | What evidence would make a generated draft useful and trustworthy? | What would make the analyst reject it? | Analyst acceptance criteria | Non-functional | High | MVP | Define trust requirements | Not Asked
48 | QA Reviewers | Quality assurance | Return drivers | QA returns may be preventable. | Show three common reasons reviews are returned. | Which checks are deterministic and which require judgment? | QA samples and checklist | Evaluation | High | MVP | Define quality checks | Not Asked
49 | QA Reviewers | Quality assurance | Evaluation labels | QA can establish expected outcomes for historical cases. | How should disputed or ambiguous cases be labeled for evaluation? | Who adjudicates disagreements? | QA adjudication process | Evaluation | High | MVP | Define ground-truth process | Not Asked
50 | Security | Information security | Threat model | Customer documents and external content may contain malicious instructions. | How should prompt injection and untrusted content be handled? | Which tool actions need isolation, confirmation or blocking? | AI threat model and security standards | Security | High | MVP | Define agent security controls | Not Asked
51 | Security | Information security | Incident response | AI incidents require a named response path. | Who can disable the agent and what events trigger that action? | What records are required for investigation? | Incident and kill-switch procedure | Security | High | MVP | Define shutdown process | Not Asked
52 | Enterprise Architecture | Architecture | Standards alignment | The POC should use approved integration and hosting patterns. | Which existing platform standards should the solution use? | Which exceptions would require architecture approval? | Reference architectures and standards | Technical | High | MVP | Confirm architecture pattern | Not Asked
53 | Model Risk | Model governance | Governance classification | The solution may be subject to model-risk assessment. | How will VGB classify the Claude-assisted workflow? | What documentation, testing and approvals are required? | Model-risk policy and intake process | Risk / Control | High | MVP | Define model governance path | Not Asked
54 | Platform Operations | Production operations | Support model | A production path needs monitoring and ownership. | Who monitors, supports and restores the service? | What availability, recovery and escalation targets apply? | Support and operational standards | Ownership | High | MVP | Define operating model | Not Asked
55 | Legal / Privacy | Legal and privacy | Processing constraints | KYC data processing may be contractually or legally constrained. | What restrictions apply to processing customer data with an external model service? | What notices, agreements or assessments are required? | Privacy and legal assessment requirements | Risk / Control | High | MVP | Confirm legal constraints | Not Asked

## Interview Tracker
Stakeholder / SME | Role | Interview Objective | Opening Playback / Hypothesis | Evidence to Request | Decision Expected | Meeting Status | Interview Owner | Date | Key Outcome | Follow-up
Victor Ong | COO | Executive outcome, risk appetite and expansion gate | Backlog creates regulatory and growth risk; MVP should reduce effort without transferring final accountability. | Executive success measures; remediation commitments; decision path | Success criteria, stop conditions and decision owner | Not Scheduled
Grace Lim | Head of Financial Crime Operations | Actual workflow, bottleneck and demo case | Effort may be concentrated in evidence collection, comparison and narrative preparation. | Recent review; slow case; QA return; queue metrics; SOP | Priority workflow step and demo scenario | Not Scheduled
Raj Menon | Deputy MLRO | Compliance controls and human authority | Claude may retrieve, compare and draft; disposition remains subject to VGB approval. | Difficult case; policy; evidence package; audit requirements | Control boundary and compliance gate | Not Scheduled
Ben Tan | Head of Data Platform Engineering | Data, runtime, region, identity and feasibility | Selected workflow requires named sources and an approved model/runtime path. | Source inventory; architecture standards; cloud/region; identity; logs | Feasible POC boundary and dependency owners | Not Scheduled
Anna Cruz | Vendor Management | Commercial baseline and cost per review | Comparison should include vendor fees, internal effort, QA and rework. | Fee schedule; case mix; internal effort; relevant contract terms | Commercial baseline and target | Not Scheduled
KYC Analysts | Front-line reviewers | Real work, exceptions and usability | Undocumented workarounds and trust needs will shape the MVP. | Screen walkthroughs; recent cases; manual workarounds | Validated task and user experience | Not Scheduled
QA Reviewers | Quality assurance | Return drivers and evaluation labels | QA examples can define quality criteria and golden cases. | Returned reviews; checklist; adjudication process | Quality checks and ground truth | Not Scheduled
Security | Information security | Threat model, control and incident response | Untrusted content and tool use require explicit controls. | AI security standards; incident and kill-switch procedures | Security control set | Not Scheduled
Enterprise Architecture | Architecture | Standards and approved patterns | The POC should align to existing integration and hosting standards. | Reference architecture; exception process | Approved architecture pattern | Not Scheduled
Model Risk | Model governance | Classification and approval path | The workflow may require model-risk governance. | Model-risk policy; intake and testing requirements | Governance path | Not Scheduled
Platform Operations | Production operations | Support and service ownership | A production path needs monitoring, recovery and support ownership. | Support model; availability and recovery standards | Operating model | Not Scheduled
Legal / Privacy | Legal and privacy | Processing and contractual constraints | External model processing may require specific assessments or terms. | Privacy assessment; contractual requirements | Legal constraints | Not Scheduled

## Decision Log
Decision ID | Decision Area | Decision Required | Options Considered | Decision | Rationale / Evidence | Decision Owner | Status | Target Phase | Dependencies | Source Stakeholder
1 | MVP Scope | Which KYC workflow step will the POC prove? | Evidence retrieval; change detection; narrative drafting; broader orchestration |  |  |  | Open | MVP | Case and data availability | Grace Lim / Raj Menon
2 | Architecture | What is the simplest sufficient architecture? | Prompt + retrieval; workflow + Claude; constrained agent; multi-agent |  |  |  | Open | MVP | Observed workflow variability | Ben Tan / Enterprise Architecture
3 | Human Authority | Which actions are allowed, confirmation-gated or prohibited? | Retrieve through approve authority matrix |  |  |  | Open | MVP | Compliance approval | Raj Menon
4 | Runtime / Model Access | Where will runtime and Claude access operate? | Direct Anthropic; approved cloud path; other approved pattern |  |  |  | Open | MVP | Cloud, network and region approval | Ben Tan
5 | Data Scope | Which sources and cases can the POC access? | Production read-only; test data; de-identified cases; synthetic cases |  |  |  | Open | MVP | Data owner approvals | Ben Tan
6 | Evaluation Gate | What thresholds and stop conditions control release? | Component checks; expert review; control tests |  |  |  | Open | MVP | Golden case set | Raj Menon / QA Reviewers
7 | Commercial Measure | How will value be measured? | Vendor fee; labor time; total cost per approved review |  |  |  | Open | MVP | Baseline data | Anna Cruz / Grace Lim

## Lists
Reference | Guidance
Workbook purpose | Working source of truth for VGB KYC Agent discovery. Use the deck for stakeholder narrative and this workbook to capture answers, requirements, decisions and follow-ups.
Discovery method | Start with a hypothesis, ask for a real example, play it back, invite correction, and use the correction to choose the next question.
Status values | Not Asked ¦ Asked ¦ Answered ¦ Follow-up Needed ¦ Closed
Requirement types | Business ¦ Functional ¦ Technical ¦ Non-functional ¦ Security ¦ Risk / Control ¦ Evaluation ¦ Commercial ¦ Ownership
Authority lens | Retrieve ¦ Compare ¦ Summarize ¦ Recommend ¦ Write ¦ Execute ¦ Approve
Architecture lens | Prompt + retrieval ¦ Workflow + Claude steps ¦ Single constrained agent ¦ Multi-agent only if specialization is proven
Source basis | User-provided VGB handover; Presentation2.pptx technical discovery class notes; Anthropic Building Effective AI Agents framework referenced in the deck.